## Neocom Daily Update
NEOCOM SITE UPDATE
Site Name: | Bellevue Manor |  |  | Date: | 4.11.18
Carrier: | Verizon |  |  | Project: | Pre Integration
Twr Owner Login Time: | 10:45 |  |  | Twr Owner Logout Time: |  | 19:00
Twr Owner Login Tech: | N/A |  |  | Twr Owner Logout Tech: |  | N/A
Cell Tech Login Time: | N/A |  |  | Cell Tech Logout Time: |  | N/A
Cell Tech Login Name: | N/A |  |  | Cell Tech Logout Name: |  | N/A
NOC Login Time: | N/A |  |  | NOC Logout Time: |  | N/A
NOC Login Tech: | N/A |  |  | NOC Logout Tech: |  | N/A
Switch Login Time: | N/A |  |  | Switch Logout Time: |  | N/A
Switch Login Tech: | N/A |  |  | Switch Logout Tech: |  | N/A
IVR Login Time: | N/A |  |  | IVR Logout Time: |  | N/A
IVR Login Tech: | N/A |  |  | IVR Logout Tech: |  | N/A
Pre Alarm Report: | N/A |  |  | Post Alarm Report: |  | N/A
Log Book Signed: | N/A |  |  | Doors/Cabinets locked: |  | N/A
| Ground Crew |  |  | Tower Crew
Name (list names of all) | Names removed |  |  | Name removed
# of Crew Members | 2 |  |  | 2
TIMELINE | Installed GPS, 6601. 3 fibers for LTE, 3 fibers for AWS, 1 orange fiber for SAR. All the material was on site. Started pre-integration but unable to complete due to bad LTE gamma secondary radio. Alarm Tested. Issues Corrected: -Alpha LTE fiber wasn't plugged in up top to 2212 -Gamma LTE fiber wasn't plugged in up top to 2212
DATA UPLOADED
|  | Y | GROUND PHOTOS |  | Y | TOWER PHOTOS
|  | Y | PRE-INTEGRATION DATA |  | N | SWEEP TESTS
|  | N | PIM TESTS |  | N | OTDR TESTS
|  | N | FIBER SCOPE TESTS |  | N | FIBER dB LOSS TESTS
|  | Y | JSA
ISSUES
COMMENTS